## Sheet1
S.No | Task description | Effort (days) | Effort (hours) | Start Date | End Date | Owner | Comments/Assumptions | Status
1 | Analyse the requirement and create task list | 0.5 | 4 | 2014-12-04 | 2014-12-04 | lichong |  | Completed
2 | Wearable device selection; purchase research: 1. smart watches 2. smart health/sports digital device development research: 1. Android/iOS SDK 2. Document and demo research 3. Hybris integration research | 4 | 36 | 2014-12-05 | 2014-12-10 | liubin | during the progress, we will send a research report and purchase plan | Completed
3 | Make lib for QRScan and iBeacons | 4 | 24 | 2014-12-11 | 2014-12-16 | liubin&zhangxiaodong |  | Completed
4 | Investigat the Jawbone & Nick API, select wearable device | 4 | 32 | 2014-12-17 | 2014-12-23 | liubin&zhangxiaodong | IDC want to use Nick+, but SDK can't get | Completed
5 | Create Jawbone Login View base on app of Q1 and Jawbone developer account | 6 | 48 | 2014-12-24 | 2014-12-31 | liubin | Send the Screenshot to IDC which is Jawbone Login View. | Completed
6 | crossplatform(iOS & Android) design, e.g. same outlook, same data structure, same UX etc. | 2 | 18 | 2015-01-05 | to the end | liubin&zhangxiaodong | need help of design team, discuss with Android team | In Progress
7 | design Hybris data structure and integration plan (coorparating with IDC team) | 1 | 9 | ? | ? | IDC |  | In Progress
8 | create new views in native iOS app with UI design | 4 | 36 | 2015-01-05 | to the end | liubin&zhangxiaodong
9 | Based on the app of Q1, create a native iOS app connecting to the selected wearable device |  |  |  |  | liubin&zhangxiaodong
10 | improve the iOS app, collecting user activity and body information and exchanging data with web service |  |  |  |  | liubin&zhangxiaodong
11 | improve the iOS app, coworking with iBeacon and GPS |  |  |  |  | liubin&zhangxiaodong
12 | integration with Hybris and local test |  |  |  |  | liubin&zhangxiaodong
13 | demo and test with IDC team |  |  |  |  | IDC
|  | 25.5 | 207