## Sheet1
S.No | Task description | Effort (days) | Effort (hours) | Start Date | End Date | Owner | Comments/Assumptions | Status
1 | Analyse the requirement and create task list | 0.5 | 4 | 2014-12-04 | 2014-12-04 | lichong |  | Completed
2 | Wearable device selection; purchase research: 1. smart watches 2. smart health/sports digital device development research: 1. Android/iOS SDK 2. Document and demo research 3. Hybris integration research | 4 | 36 | 2014-12-05 | 2014-12-10 | liubin | during the progress, we will send a research report and purchase plan | Completed
3 | crossplatform(iOS & Android) design, e.g. same outlook, same data structure, same UX etc. | 2 | 18 |  |  | liubin | need help of design team, discuss with Android team | In Progress
4 | design Hybris data structure and integration plan (coorparating with IDC team) | 1 | 9 |  |  | IDC |  | In Progress
5 | create new views in native iOS app with UI design | 4 | 36 |  |  | zhangxiaodong
6 | Based on the app of Q1, create a native iOS app connecting to the selected wearable device | 1 | 9 |  |  | liubin
7 | improve the iOS app, collecting user activity and body information and exchanging data with web service | 3 | 27 |  |  | liubin
8 | improve the iOS app, coworking with iBeacon and GPS | 2 | 18 |  |  | zhangxiaodong
9 | integration with Hybris and local test | 3 | 27 |  |  | both
10 | demo and test with IDC team | 4 | 36 |  |  | IDC
|  | 24.5 | 220