## Sheet1
S.No | Task description | Effort (days) | Start Date | End Date | Owner | Comments/Assumptions | Status | issues
1 | Set up Hybris environment | 2 | 2014-05-11 | 2014-06-11 | Vijayanand | No failures in build, and should work as mentioned in doc. | Started | Download failed many times and waiting till end of day to get internal shared bigfile.
2 | Android SDK | 2 | 2014-07-11 | 2014-09-11 | Vijayanand | Checking the android app on device and trying out inclusion of ext lib for feasibility study
3 | QR code UI design based on UX inputs | 1 | 2014-10-11 | 2014-11-11 | Vijayanand | Updating the screen part of android src. Assuming the app on android works fine without any issue.
4 | QR Decoder library integration | 3 | 2014-11-11 | 14/11/14 | Vijayanand | Integrating the ext library and building the app for android